## Roadmap
| STUDIO | PRODUCT | FRONTEND | GRAPHICS | ANIMATION | SOUND | SERVER | QA | Automation QA | CERT REP | START DATE | CERT DATE | FREEZE | EXCL DATE | LIVE DATE | Certificates | 2W PLAYER AVE | GAME-GUESS AVG | DELTA | VARIANCE | MAX WIN CAP | COMMENT | TO DISCUSS
Creepy Carnival |  | Jonas, Emil | Emil | Nico | Nico | External | John | [7 empty] | 2015-05-26
Creepy Carnival (mobile) |  | Jonas, Emil | Emil | Nico | Nico | External | Jonas | [7 empty] | 2015-12-02
Space Arcade |  | Per, Wai | External | Nico | Nico | David | John | [7 empty] | 2016-08-31 |  |  |  |  | 16
Oktoberfest |  | Per, Wai | Emil | Nico | Nico | David | Wai | [7 empty] | 2016-11-15 |  | 156.92 |  |  | 37
Kitchen Drama Sushi Mania |  | Per, Wai | External | Nico | Nico | David | Wai | [7 empty] | 2017-04-12 |  | 178.7 |  |  | 31
Wixx |  | Per, Wai | Ning | Lorenzo | Lorenzo | David | Wai | [7 empty] | 2017-10-31 |  | 107.45 |  |  | 61
Kitchen Drama BBQ Frenzy |  | Per, Wai | Jonas W | Nico | Nico | David | Wai | [7 empty] | 2017-11-29 |  | 74.04 |  |  | 31
Casino Win Spin |  | Per, Wai | Jie, Antonio | Artem | Artem | David | Wai | [7 empty] | 2018-01-31 |  | 127.77 |  |  | 55
Tesla Jolt |  | Per, Wai | Hevar, Jonas W | Nousseir | Nousseir | David | Wai | [7 empty] | 2018-03-29 |  | 115.02 |  |  | 28
Coins of Fortune |  | Per, Wai | Jie, Antonio | Artem | Artem | David | Wai | [7 empty] | 2018-06-28 |  | 109.58 |  |  | 54
Hot Nudge |  | Per, Wai | Ning, Alican | Lorenzo | Lorenzo | David | Wai | [7 empty] | 2018-07-26 |  | 175.18 |  |  | 70
Dungeon Quest |  | Per, Wai | Jonas W | Nico | Nico | David | Wai | [7 empty] | 2018-09-27 |  | 69.11 |  |  | 38
Ice Ice Yeti |  | Per, Wai | Jerker, Ning | Nico | Nico | David | Wai | [7 empty] | 2018-11-15 |  | 67.21 |  |  | 117
Fruits |  | Per, Wai | Alican, Hevar | Artem | Artem | David | Wai | [7 empty] | 2019-01-30 |  | 146.39 |  |  | 55
Owls |  | Per, Wai | Jie, Antonio | Nico | Nico | David | Wai | [7 empty] | 2019-02-27 |  | 61.81 |  |  | 41
Starstruck |  | Per, Jonas | Jie, Antonio | Artem | Artem | David | Wai | [6 empty] | 2019-03-18 | 2019-03-27 |  | 98.69 |  |  | 47 |  | Exclusive at ComeOn
Tombstone |  | Per, Wai | Ning | Lorenzo | Lorenzo | David | Wai | [6 empty] | 2019-04-18 | 2019-05-02 |  | 84.39 |  |  | 366 |  | Exclusive at LeoVegas
Mayan Magic Wildfire |  | Emil, Per | Jonas W, Amit | Jan | Jan | David | Wai | [7 empty] | 2019-06-04 |  | 76.67 |  |  | 40
Tractor Beam |  | Emil, Per | Antonio | Nico | Nico | David | Wai | [7 empty] | 2019-07-02 |  | 81.26 |  |  | 166
The Creepy Carnival (remake) |  | n/a | India | Gustav | Gustav | David | Wai | [7 empty] | 2019-07-16 |  | 80.99 |  |  | 35
Thor Hammer Time |  | Emil, Per | Jerker | Carlo | Pernilla | David | Wai |  |  |  |  | 2019-07-01 |  | 2019-07-18 | 2019-08-01 |  | 77.63 |  |  | 64 |  | Exclusive on Kindred
Hot 4 Cash |  | Jonas, Wai | Seb | Artem | Artem | David | Wai |  |  |  |  | 2019-07-15 |  | 2019-07-31 | 2019-08-15 |  | 93.67 |  |  | 81 |  | Exclusive on Rizk
Pixies vs Pirates |  | Emil, Per | Ning | Chrissa | Chrissa | David | Wai |  |  |  |  | 2019-08-03 |  | 2019-08-20 | 2019-09-03 |  | 94.59 |  |  | 111 |  | Exclusive on Mr Green
Manhattan Goes Wild |  | Emil, Per | Alican | Jan | Pernilla | External | Wai |  |  |  |  | 2019-09-02 |  | 2019-09-18 | 2019-10-02 |  | 105.63 |  |  | 88 |  | Exclusive on Betsson
Tomb of Nefertiti |  | Jonas, Wai | Shika, Pradeep | Carlo | Anoop | External | Wai |  |  |  |  | 2019-10-05 |  | 2019-10-22 | 2019-11-05 |  | 118.46 |  |  | 73 |  | Exclusive on Bitstarz
Dragon Tribe |  | Emil, Per | Jie | Kit | Kit | David | Wai |  |  |  |  | 2019-11-12 |  | 2019-11-28 | 2019-12-12 |  | 126.62 |  |  | 115 |  | Exclusive with Dumarca
Poison Eve |  | Jonas, Wai | Guarav | Javi | Gustav | David | Wai |  |  |  |  | 2020-01-07 |  | 2019-12-23 | 2020-01-07 |  | 71.49 |  |  | 86 |  | Exclusive Playfortuna
Punk Rocker |  | Jonas, Wai | Seb | Artem | Artem | David | Wai |  |  |  |  | 2020-01-12 |  |  | 2020-02-12 |  | 197.8 |  |  | 99
Barbarian Fury |  | Jonas, Wai | Pradeep | Anoop | Anoop | David | Wai |  |  |  |  | 2020-03-03 |  | 2020-02-18 | 2020-03-03 |  | 203.06 |  |  | 100 |  | Exclusive on Rizk
Gaelic Gold |  | Emil, Per | Jie | Chrissa | Chrissa | David | Wai |  |  |  |  | 2020-02-16 |  |  | 2020-03-16 |  | 56.73 |  |  | 70
Harlequin Carnival |  | Emil, Per | Antonio | Jan | Jan | David | Wai |  |  |  |  | 2020-04-07 |  |  | 2020-04-07 |  | 111.2 |  |  | 106
Deadwood xNudge |  | Jonas, Wai | Ning | Carlo | Meng | David | Wai |  |  |  |  | 2020-04-04 |  | 2020-04-22 | 2020-05-06 |  | 248.64 |  |  | 281 |  | Exclusive on Leo
Bonus Bunnies |  | Emil, Per | Jerker | Kit, (Javi) | Kit | David | Wai |  |  |  |  | 2020-04-23 |  | 2020-05-26 | 2020-06-09 |  | 118.38 |  |  | 82 |  | Value is 2 weeks global. Exclusive on ATG(Bug)
Milky Ways |  | Jonas, Wai | Amit | Gustav | Gustav | David | Wai |  |  |  |  | 2020-05-10 |  |  | 2020-06-24 |  | 85.66 |  |  | 75
Golden Genie |  | Jonas, Wai | Pankaj | Javi | Satish | David | Wai |  |  |  |  | 2020-05-15 |  | 2020-06-23 | 2020-07-07 |  | 163.26 |  |  | 99 |  | Exclusive William Hill - CONF
Immortal Fruits |  | Emil, Per | Shikha | Javi | Satish | David | Wai |  |  |  |  | 2020-06-29 |  | 2020-07-21 | 2020-08-04 |  | 103.93 |  |  | 147 |  | Floater - Replaces Golden Goblins | Tipico - presented (semi-confirmed)
Book of Shadows |  | Emil, Per | Pradeep | Chrissa | Chrissa | External | Wai |  |  |  |  | 2020-07-13 |  | 2020-08-06 | 2020-08-20 |  | 105.29 |  |  | 241 |  | Book of inspired | Wildz - presented (semi-confirmed)
Buffalo Hunter |  | Emil, Per | Antonio | Carlo | Satish | External | Wai |  |  |  |  | 2020-07-20 |  | 2020-08-26 | 2020-09-08 |  | 105.69 | 119.4 | -13.71 | 125 |  | 3 bonuses, same triggers. | Tipico? (Casumo?)
Monkey's Gold | Labs | Emil, Per | Jerker | Anoop | Anoop | David | Wai |  |  |  |  | 2020-09-11 |  |  | 2020-10-13 |  | 131.85 | 130.1 | 1.75 | 72 |  | xPays | No exclusivity
Warrior Graveyard | Nolimit | Jonas, Wai | Raman | Anuj | Satish | David | Wai |  |  |  |  | 2020-10-14 |  |  | 2020-11-03 |  | 186.55 | 161 | 25.55 | 88 |  | Hot nudge/Barbarian inspired | ComeOn/Cherry?
Tomb of Akhenaten | Nolimit | Jonas, Wai | Gaurav, (Pankaj) | Carlo | Anoop | David | Wai |  |  |  |  | 2020-10-21 |  | 2020-12-01 | 2020-12-15 |  | 130.92 | 147.4 | -16.48 | 83 |  | Tomb of Nefertiti follow up (theme inspired) | Bitstarz exclusive
San Quentin | Over the limit | Jonas, Wai | Seb | Artem | Artem | David | Wai |  |  |  |  | 2020-12-11 |  |  | 2021-01-12 |  | 200.4 | 189 | 11.4 | 184 | 150000x
East Coast vs West Coast | Nolimit | Emil, Per | Jonas W | Jan | Jan | David | Wai |  |  |  |  | 2020-12-15 |  |  | 2021-02-02 |  | 165.31 | 195.7 | -30.39 | 175 | 30618x | Punk rocker inspired w. infectious xWays
Fire in the hole | Nolimit | Jonas, (Wai) | Pradeep | Kit | Kit | David | Wai |  |  |  |  | 2021-02-01 |  |  | 2021-03-02 |  | 311.22 | 175.3 | 135.92 | 369 | 60000x | ATG exclusive sweden (global release same as ATG)
Bushido Ways xNudge | Nolimit | Emil, (Jonas) | Mayank, Gaurav | Chrissa | Kunal | David | Martin, (Wai) |  |  |  |  | 2021-03-01 |  | 2021-03-30 | 2021-04-13 |  | 161.34 | 182.1 | -20.76 | 269 | 30000x | ATG + Hero Gaming all markets excl SE.
El Paso Gunfight xNudge | Nolimit | Jonas, (Wai) | Ning | Carlo | Meng | Viktor ( & David) | Wai |  |  |  |  | 2021-03-19 |  | 2021-04-20 | 2021-05-04 |  | 201.45 | 239 | -37.55 | 655 | 44440x | Rootz Limited | Exclusive on Rootz
Infectious 5 xWays | Nolimit | Per | Shikha, Pradeep | Javi | Satish | David | Wai |  |  |  |  | 2021-04-20 |  | 2021-05-18 | 2021-06-01 |  | 160.13 | 196.4 | -36.27 | 614 | 55555x | ATG + non swede operator exclusive (STAKE via DAMA) | Exclusive release on 18th - customers aware.
xWays Hoarder xSplit | Nolimit | Wai | Seb | Artem, Gustav | Gustav | David | Wai |  |  |  |  | 2021-05-05 |  | 2021-06-22 | 2021-07-06 |  | 238.68 | 207 | 31.68 | 272 | 11030x | iGP MGA Brands
Mental | Over the limit | Jonas, Jaiveer | Raman, Pankaj | Anoop | Anoop | Viktor | Pankaj (Wai) |  |  |  |  | 2021-07-16 |  | 2021-08-03 | 2021-08-31 |  | 368.21 | 201.6 | 166.61 | 896 | 66666x | No ATG (won't make it in time - customer informed)
Das xBoot | Nolimit | Emil | Jonas W | Jan | Jan | David | Martin |  |  |  |  | 2021-07-30 |  |  | 2021-09-14 |  | 277.75 | 217.8 | 59.95 | 352 | 55200x | moved 1 week, player value without DX3 which is less 1% bet. would be 266
Evil Goblins xBomb | Nolimit | Per | Jie | Carlo | Kunal | David | Martin |  |  |  |  | 2021-07-30 |  | 2021-09-28 | 2021-10-12 |  | 158.03 | 214.3 | -56.27 | 362 | 31969x | ATG - moved 1 week, ATG informed
Legion X | Nolimit | Emil | Antonio, Raman | Christina | Christina | Viktor | Wai |  |  |  |  | 2021-10-19 |  |  | 2021-11-30 |  | 166.98 | 202.15 | -35.17 | 715 | 31000x | Moved to the 30th November - Please update
True Grit | Nolimit | Jonas | Jerker, Jonas W | Nico | Nico | David | Martin |  |  |  |  | 2021-11-12 |  |  | 2021-12-21 |  | 220.5 | 204.33 | 16.17 | 393 | 20220x | Moved to 21/12 | COOLBET?
Tombstone R.I.P | Over the limit | Jonas | Ning | Javi | Meng | Viktor | Wai |  |  |  |  | 2021-12-15 |  |  | 2022-01-11 |  | 195.89 | 270.53 | -74.64 | 4469 | 300000x | LeoVegas, Unibet, GVC/Entain not released. ComeOn took it down after a week
Punk Toilet | Nolimit | Jonas | Seb | Artem | Artem | David | Yuhan |  |  |  |  | 2022-01-12 |  |  | 2022-02-08 |  | 185.03 | 218.24 | -33.21 | 623 | 33333x
Misery mining (FITH 2) | Nolimit | Jonas | Gaurav, Pankaj | Kit | Kit | Viktor | Martin | Shivangi |  |  |  | 2022-02-22 |  |  | 2022-03-15 |  | 278.29 | 249.05 | 29.24 | 365 | 70000x
Remember Gulag | Nolimit | Per | Jonas W | Jan | Kunal | Lars | Yuhan | Priya, Pankaj |  |  |  | 2022-03-15 | 2022-04-19 |  | 2022-04-19 |  | 217.58 | 223.94 | -6.36 | 412 | 30000x | Some Casino not taking it
Karen Maneater (Hoarder 2) | Nolimit | Wai | Shikha, Vishnu | Chrissa | Gustav | Viktor | Wai | Vinita |  |  |  | 2022-04-08 | 2022-04-19 |  | 2022-05-10 |  | 140.64 | 224.01 | -83.37 | 1327 | 11757x
Folsom Prison (SQ 2) | Nolimit | Jonas/Wai | Pradeep | Omkar | Kunal | Lars | Martin | Shivangi, Pankaj |  |  |  | 2022-05-16 |  |  | 2022-06-14 |  | 151.87 | 236.2 | -84.33 | 1892 | 75000x
The Rave | Nolimit | Per | Jie, Antonio | Carlo | Meng | Viktor, David | Yuhan | Priya |  |  |  | 2022-05-20 |  |  | 2022-07-12 |  | 125.72 | 187 | -61.28 | 749 | 41500x | moved one week
Road Rage | Labs | Seb | Seb | Nico(Artem) | Nico(Artem) | Lars | Wai | Vinita, George |  |  |  | 2022-07-18 |  |  | 2022-08-16 |  | 184.42 | 149.1 | 35.32 | 284 | 36000x
The Border | Nolimit | Emil | Jerker | Diksha, Deepak | Surender | Viktor | Martin | Priya, Pankaj |  |  |  | 2022-08-15 |  |  | 2022-09-13 |  | 164.95 | 203.6 | -38.65 | 394 | 44288x | DDOS
Little Bighorn | Nolimit | Wai | Vishnu | Anoop | Anoop/Surender | Lars | Wai | Shivangi |  |  |  | 2022-09-12 |  |  | 2022-10-11 |  | 107.07 | 180.9 | -73.83 | 652 | 25676x
Serial | Over the limit | Per | Ning | Javi | Meng | Lars | Yuhan | George (Vinita) |  |  |  | 2022-09-16 | 2022-10-25 |  | 2022-11-08 |  | 136.57 | 204.5 | -67.93 | 1872 | 74800x | Some Casino not taking it
Rock Bottom | Nolimit | Wai | Gaurav, Shivay | Carlo | Kunal | Lars | Wai | Shivangi (Pankaj) |  |  |  | 2022-10-21 |  |  | 2022-11-22 |  | 134.86 | 166.6 | -31.74 | 177 | 19690x
Pearl Harbor (xBoot 2) | Nolimit | Emil | Jie | Jan | Gustav | David | Martin | George (Jaiveer) |  |  |  | 2022-11-04 |  |  | 2022-12-07 |  | 160.62 | 150 | 10.62 | 356 | 41127x | Release on Dec 7th, on the actual date of Pearl Harbor attack
Dead Canary | Nolimit | Per | Jonas W | Kit | Kit, Surender | Viktor | Yuhan | Pankaj |  |  |  | 2022-11-18 | 2022-11-08 |  | 2022-12-20 | 2022-12-16 | 187.26 | 202.5 | -15.24 | 723 | 65000x
Walk of Shame | Nolimit | Wai | Pradeep | Deepak, Carlo | Ed/Meng | Viktor | Wai | Shivangi | Anil |  |  | 2022-12-05 |  |  | 2023-01-17 | 2023-01-10 | 92.83 | 142.5 | -49.67 | 207 | 9822x
Benji killed in Vegas (EvsW2) | Nolimit | Emil | Jerker | Jerker | Artem/Annie | David | Martin | Pankaj | Anil |  |  | 2023-01-12 |  |  | 2023-02-07 | 2023-02-03 | 130.8 | 160.4 | -29.6 | 154 | 10000x
Blood & Shadow | Nolimit | Seb | Jonas W, Antonio, Shivay | Chrissa | Chrissa, Gustav | Viktor | Wai/Iman | Shivangi, Claudia | Anil |  |  | 2023-02-09 |  |  | 2023-03-07 | 2023-03-07 | 154.09 | 148.2 | 5.89 | 69 | 6666x | Max bet: 280
Kiss My Chainsaw | Nolimit | Seb | Manish, Pankaj | Raj, Deepak K | Surender | David | Martin | Pankaj, Sonali | Anil |  |  | 2023-03-07 |  |  | 2023-04-11 | 2023-03-29 | 86.22 | 131.3 | -45.08 | 157 | 10900x | Max bet: 200
Disturbed (Mental 2 pre) | Over the limit | Lars | Gaurav, Virender | Vijay | Jitender | Lars | Wai | Shivangi | Anil |  |  | 2023-03-31 |  |  | 2023-05-09 | 2023-05-02 | 111.38 | 154.5 | -43.12 | 765 | 54391x | Max bet: 100
Whacked! | Nolimit | Per | Sandru, Sergiu | Marco | Christina Erdei | Lars | Yuhan | George | Anil |  |  | 2023-04-19 |  |  | 2023-05-23 | 2023-05-16 | 85.68 |  |  | 305 | 11912x | Max bet: 200
Gluttony | Nolimit | Seb | Vishnu | Aniruddha, Alok | Surender, Prakash | Viktor | Wai/Iman | Claudia | Anil |  |  | 2023-04-27 |  |  | 2023-06-06 | 2023-05-22 | 101.43 |  |  | 254 | 32000x | Max bet: 100
The Cage | Nolimit | Per | Viktor | Annie, Jan | Annie | David | Yuhan | Pankaj, Sonali | Anil |  |  | 2023-05-01 |  |  | 2023-06-20 | 2023-06-12 | 84.02 |  |  | 216 | 25000x | Max bet: 200
Bounty Hunter xNudge | Nolimit | Wai | Jerker | Carlo | Ed | Viktor | Wai | Shivangi, Sahil | Anil |  |  | 2023-06-12 |  |  | 2023-07-11 | 2023-06-29 | 112.96 |  |  | 564 | 52310x | Max bet: 100
True Kult | Nolimit | Per | Ning | Javi | Meng | Lars | Yuhan | Sonali, Sadhika | Anil |  |  | 2023-06-19 |  |  | 2023-08-08 | 2023-07-27 | 106.22 |  |  | 413 | 23237x | Max bet: 100
DJ P5ychØ | Labs | Krisztian | Pradeep, Prachi | Artem | Artem | David | Martin | Claudia | Anil |  |  | 2023-06-23 |  |  | 2023-08-22 | 2023-07-19 | 68.34 |  |  | 210 | 25420x | Max bet:100
The Crypt | Nolimit | Per | Jie | Kit | Gustav | Viktor | Iman | Shivangi | Anil |  |  | 2023-07-10 |  |  | 2023-09-05 | 2023-08-18 | 120.45 |  |  | 350 | 27000x | Max bet: 100
Space Donkey | Labs | Wai | Shivay, Prachi | Anoop | Anoop | David | Martin | Pankaj, Sahil | Anil, Shamim |  |  | 2023-08-28 |  |  | 2023-10-03 |  | 104 |  |  | 106 | 14649x | Max bet: 200
Ugliest Catch | Nolimit | Krisztian | Sandru | Marco/Carlo | Christina Erdei | Viktor | Jasper/Martin | Sonali | Shamim, Himanshu |  |  | 2023-09-08 |  |  | 2023-10-17 |  | 105.18 |  |  | 727 | 50000x | Max bet: 100
Roadkill | Labs | Seb | Pankaj, Virender | Nico | Nico/(Gustav) | Lars | Yuhan | Claudia, Sadhika | Shamim, Anil |  |  | 2023-09-26 |  |  | 2023-11-07 |  | 59.82 |  |  | 178 | 11091x | Max bet: 200
Nine To Five | Labs | Lars | Viktor | Artem | Artem | Lars | Jasper | Shivangi, Nilesh | Himanshu, Anil |  |  | 2023-10-04 |  |  | 2023-11-21 |  | 166.51 |  |  | 936 | 9217x | Max bet: 280
Jingle Balls | Nolimit | Per | Jonas W | Jan | Jan | Lars | Yuhan | Pankaj | Anil |  |  | 2023-10-23 |  |  | 2023-12-05 |  | 74.39 |  |  | 320 | 12250x | Max bet: 200
Devil's Crossroad | Nolimit | Wai/Gary | Antonio, Shivay | Annie | Annie, (Christina) | Viktor | Iman | Sonali (Jaiveer) | Anil |  |  | 2023-11-13 |  |  | 2024-01-09 | MOVED TO JAN | 75.97 |  |  | 220 | 13180x | Max bet: 200
Land of the free | Nolimit | Lars | Gaurav, Manish | Vijay, Alok | Prakash | Lars | Yuhan | Claudia (Sadhika) | Shamim |  |  | 2023-12-04 |  |  | 2024-01-23 |  | 150.34 |  |  | 614 | 57k | Max bet: 100
D Day | Nolimit | Krisztian | Vishnu | Carlo | Ed | Viktor | Jasper | Shivangi | Himanshu |  |  | 2023-12-11 |  |  | 2024-02-13 |  | 111.86 |  |  | 444 | 55k | Max bet: 100
FITH 2 | Nolimit | Gary | Jie | Kit | Kit | Victor 2 | Jasper | Nilesh | Himanshu |  |  | 2023-12-18 |  |  | 2024-02-20 |  | 153.62 |  |  | 796 | 65k | Max bet: 100
Possessed | Nolimit | Krisztian | Oliver (Viktor) | Javi | Meng | Viktor | Iman | Sadhika | Shamim |  |  | 2024-02-02 |  |  | 2024-03-05 |  | 94.9 |  |  | 666 | 50k | Max bet: 100
Brick Snake 2000 | Labs | Lars | Viktor | Artem | Artem | Lars | Jasper | Pankaj | Anil |  |  | 2024-02-12 |  |  | 2024-03-21 | MOVED - MALTA PH | 104.51 |  |  | 847 | 8110x /16220x | Max bet: 280
Tombstone No Mercy | Nolimit | Per/Wai | Antonio | Javi | Ed | Viktor | Christian | Pankaj | Anil |  |  | 2024-03-07 |  |  | 2024-04-16 | 10c - moved 1w, Gamdom exkl | 99.18 |  |  | 430 | 16480x | Max bet: 100
Kenneth must die | Over the limit | Jonas | Pradeep | Anoop, Alok | Anoop | Lars | Pankaj (Wai) | Shivangi (Denis) | Himanshu |  |  | 2024-04-08 |  |  | 2024-05-07 | MOVE! Cap Win issues. | 179.77 |  |  | 842 | 69000x | Max bet: 100
Loner | Nolimit | Lars | Jerker, Virender (AS) | Vijay | Gustav | Lars | Wai | Claudia | Anil |  |  | 2024-04-24 |  |  | 2024-05-21 |  | 151.57 |  |  | 349 | 14999x | Max bet: 200
Deadwood RIP | Over the limit | Per/Wai | Ning | Carlo | Meng | Viktor | Yuhan | Nilesh | Anil |  |  | 2024-06-04 |  |  | 2024-06-04 | 10c | 204.07 |  |  | 688 | 100000x | Max bet: 100
Beheaded | Nolimit | Seb | Sergiu, Vishnu (Seb) | Aniruddha, (Javi AD) | Christina | Viktor | Iman | Sonali | Shamim | Alex |  | 2024-04-24 |  |  | 2024-06-18 |  | 120.98 |  |  | 1430 | 15950x | Max bet: 280
Punk Rocker 2 | Nolimit | Tiger | Gaurav (Jie) | Annie, Artem (AD) | Prakash, Gustav | David | Yuhan | Priya, Sadhika | Anil | Laurentiu/Alex |  | 2024-05-28 |  |  | 2024-07-09 |  | 216.78 |  |  | 614 | 30144x | Max bet: 100
Apocalypse Super xNudge | Nolimit | Krisztian | Sandru | Marco | Christina, Victoriia | Reynir | Iman | Pankaj | Shamim | Dragos/Lau |  | 2024-05-29 |  |  | 2024-07-23 |  | 136.77 |  |  | 590 | 20000x | Max bet: 200
Outsourced | Labs | Lars | Viktor | Artem | Artem | Lars | Jasper | Shivangi | Himanshu, Anil | Alex |  | 2024-06-20 |  |  | 2024-08-06 |  | 172.61 |  |  | 474 | 5000x | Max bet: 280
Stockholm Syndrome | Nolimit | Wai/Calle | Prachi+Pankaj | Jan | Prakash | Victor F | Wai/Christian | Denis | Himanshu | Laurentiu |  | 2024-05-31 |  |  | 2024-08-20 |  | 151.33 |  |  | 824 | 28873x | Max bet: 200
Skate or Die | Nolimit | Lars | Oliver | Carlo | Ed | Lars | Jasper | Claudia | Anil | Alex |  | 2024-08-06 |  |  | 2024-09-10 | Moved +1w | 142.68 |  |  | 471 | 30000x | Max bet: 100
San Quentin 2: Death Row | Over the Limit | Wai/Per | Seb | Anders | Viktoriia | David | Iman | Iman | Shamim | Laurentiu |  | 2024-08-19 |  |  | 2024-09-24 | Move +1w? | 172 |  |  | 28467 | 200000x | Max bet: 100
Brute Force | Nolimit | Krisztian | Shivay, Anubhav | Deepak, Alok | Varun | Reynir | Jasper | Priya | Himanshu | Alex |  | 2024-08-20 |  |  | 2024-10-08 |  | 260.91 |  |  | 784 | 40000x | Max bet: 100
Blood & Shadow 2 | Nolimit | Krisztian | Virender | Vijay | Varun | Viktor | Iman | Sadhika, Ankit | Himanshu | Laurentiu |  | 2024-09-10 |  |  | 2024-10-22 |  | 139.21 |  |  | 366 | 16161x | Max bet: 280
Outsourced: Slash game | Labs | Lars | Viktor | Artem | Artem | Lars | Jasper | Shivangi | Himanshu | Alex |  | 2024-10-01 |  |  | 2024-11-05 |  | 19.25 |  |  | 474 | 1500x | Max bet: 1000 (high!) (1c bet)
Munchies (Decadence), (SHORT PROD) | Labs | Tiger | Oliver | Annie | Gustav | Viktor / David | Jasper | Nilesh | Shamim | Laurentiu |  | 2024-10-17 |  |  | 2024-11-19 |  | 109.4 |  |  | 338 | 40000x
Tanked | Labs | Tiger | Pradeep, Utkarsh | Kit | Gustav, Viktoriia | Reynir | Jasper | Shivangi | Anil | Laurentiu |  | 2024-10-04 |  |  | 2024-12-03 |  | 211.33 |  |  | 237 | 25000x | Max bet: 280
Outsourced: Payday | Labs | Lars | Viktor | Artem | Artem | Lars | Jasper | Denis | Shamim | Laurentiu |  | 2024-10-23 |  |  | 2024-12-17 |  | 81.44 |  |  | 123 | 10000x | Max bet: 200
xWays Hoarder 2 | Nolimit | Tiger+Calle | Antonio, Shivay | Nico | Nico | Viktor | Iman | Denis | Himanshu | Laurentiu |  | 2024-11-11 |  |  | 2025-01-14 |  | 261.65 |  |  | 1381 | 25920x | Max bet: 200
Tombstone Slaughter: El Gordos Revenge | Over the Limit | Per/Wai | Ning | Javi | Varun, Viktoriia | Reynir | Yuhan | Claudia | Shamim |  |  | 2024-11-25 |  |  | 2025-01-28 |  | 249.92 |  |  | 2495 | 500000x | Max bet: 100 (Min bet: 10c)
Duck Hunters | Labs | Tiger/Jasper | Prachi (Gaurav) | Aniruddha | Prakash | David | Jasper | Sumit | Anil | Laurentiu |  | 2024-11-18 |  |  | 2025-02-11 |  | 452.18 |  |  | 325 | 30000x | Max bet: 280?
Dead, Dead Or Deader | Nolimit | Lars | Sandru + Sergiu | Marco | Ed, Hannah | Lars | Christian/Iman | Sadhika | Himanshu | Laurentiu |  | 2024-11-21 |  |  | 2025-02-25 | Moved +1w | 154.39 |  |  | 565 | 19349x | Max bet: 100
Home of the Brave | Over the Limit | Lars | Gaurav | Vijay | Prakash | Lars | Yuhan | Nilesh | Himanshu | Alex |  | 2025-02-05 |  |  | 2025-03-11 |  | 170.14 |  |  | 829 | 61446x | Max bet: 100
Mental 2 | Over the Limit | Lars/Jonas | Pankaj + (Pradeep) | Anoop | Anoop | Lars | Yuhan | Shivangi | Anil | Dragos |  | 2025-02-17 |  |  | 2025-03-25 |  | 249.58 |  |  | 1726 | 99999x | Max bet: 100
Blood Diamond | Nolimit | Tiger | Seb | Anders | Gustav | Victor F | Christian | Ankit | Shamim |  |  | 2025-02-27 |  |  | 2025-04-08 |  | 148.47 |  |  | 693 | 14780x | Max bet: 100
Highway to Hell | Nolimit | Per | Shivay, Akash | Denise | Ed, Hannah | David | Jasper | Denis | Shamim | Laurentiu |  | 2025-03-03 |  |  | 2025-04-22 |  | 125.99 |  |  | 286 | 20066x | Max bet: 100
Kill Em All | Labs | Tiger | Viktor | Kit | Kit & Prakash | David | Jasper, Christian | Sadhika | Shamim |  |  | 2025-04-01 |  |  | 2025-05-20 |  | 106.71 |  |  | 540 | 11916x | Max bet: 100
Fire In The Hole 3 | Nolimit | Wai | Seb | Jan | Viiktoria | Victor F | Jasper | Sumit | Himanshu |  |  | 2025-03-25 |  |  | 2025-06-03 |  | 222.13 |  |  | 957 | 70000x | Max bet: 100
Flight Mode | Nolimit | Lars | Viktor | Artem | Artem | Lars | Jasper, Christian | Nilesh | Himanshu, Arjun | Laurentiu |  | 2025-04-15 |  |  | 2025-06-17 |  | 277.83 |  |  | 75 | 5051x | Max bet: 280, S
Brute Force: Alien Onslaught | Nolimit | Krisztian | Utkarsh (Shivay) | Carlo, Francell | Hannah, Khei | Reynir | Jasper, Christian | Denis | Himanshu |  |  | 2025-05-13 |  |  | 2025-07-08 |  | 285.8 |  |  | 999 | 90000x | Max bet: 100, M
Tsar Wars | Labs | Tiger | Anubhav (Pradeep) | Annie, Carlo Felipe | Annie | Lars | Yuhan | Claudia | Shamim |  |  | 2025-06-03 |  |  | 2025-07-22 |  | 150.06 |  |  | 100 | 19775x | Max bet: 100, M
Seamen | Nolimit | Jasper | Oliver | Johan | Ed | Victor F | Jasper | Ankit | Anil, Arjun |  |  | 2025-06-11 |  |  | 2025-08-05 |  | 254.2 |  |  | 262 | 20000x | M
Gator Hunters | Nolimit | Jasper | Shivay | Vijay, Alok | Varun | Victor F | Jasper/Christian | Nilesh | Shamim |  |  | 2025-07-03 |  |  | 2025-08-19 |  | 226.75 |  |  | 402 | 25000x | M
Dead Men Walking | Nolimit | Wai, Gaurav | Akash (Gaurav) | Aniruddha, Javi (concept) | Prakash, Hironmoy | Reynir | Iman | Denis | Arjun, Himanshu |  |  | 2025-07-22 |  |  | 2025-09-09 |  | 95.15 |  |  | 402 | 25313x | M, 200 (Min bet: 10c)
Breakout | Nolimit | Tiger | Prachi, Shivay | Javi | Ed, Khei | Reynir | Christian | Ankit | Shamim |  |  | 2025-09-02 |  |  | 2025-10-14 |  | 153.95 |  |  | 182 | 20000x | M
Bangkok Hilton | Nolimit | Krisztian, Lars | Sandru, (Sergiu) | Marco | Viktoriia | Victor F | Iman | Shivangi | Himanshu |  |  | 2025-08-12 |  |  | 2025-10-28 |  | 128.11 |  |  | 743 | 44444x | M
Disorder | Nolimit | Bjarne | Virender | Anoop, Deepak | Anoop | Gum | Iman | Sumit | Himanshu |  | 2025-05-08 | 2025-09-16 |  |  | 2025-11-04 |  | 144.72 |  |  | 767 | 23500x | M
Bizarre | Nolimit | Krisztian, Bjarne | Utkarsh | Noreus, Francell (Carlo) | Hannah | Victor F | Jasper | Priya | Shamim, Arjun |  |  | 2025-09-16 |  |  | 2025-11-18 |  | 139.55 |  |  | 589 | 20000x | M
Crazy Ex-Girlfriend | Express | Lars | Oliver | Johan | Johan | Lars | Jasper | Shivangi | Himanshu, Arjun |  |  | 2025-10-14 |  |  | 2025-12-02 |  | 241.85 |  |  | 442 | 9999x | S
Duck Hunters 16K | BESPOKE | Ben | Sukhdev (Shivay) | Annie | Varun | Victor F | Jasper | Dan, Sumit | Shamim |  |  | 2025-10-07 |  |  | 2025-12-15 | UNREG. 96% and 98% Only | 778.21 |  |  | 279 | 16000x | S
Das xBoot Zwei! | Nolimit | Bjarne | Pradeep | Jan | Prakash, Hironmoy | Reynir | Christian (Wai) | Nilesh | Jasper |  | 2025-06-19 | 2025-11-04 |  |  | 2025-12-16 | Excl. Gamdom, Team Mexico (Latam), Crown (SW) | 170.46 |  |  | 652 | 59999x | M
Duck Hunters: Happy Hour | Nolimit | Jasper | Sukhdev (Shivay) | Aniruddha | Varun | Gum | Jasper | Priyanka, Nilesh | Anil, Shamim |  |  | 2025-11-18 |  |  | 2026-01-13 | All versions incl 98% | 288.88 |  |  | 375 | 33333x | S
Golden Shower | Nolimit | Wai | Gaurav, Virender | Denise | Gustav, Ed | Victor F | Iman | Ankit | Himanshu, Arjun |  |  | 2025-12-10 |  |  | 2026-01-27 |  | 145.61 |  |  | 567 | 19999x | Black friday is on the 28th of Nov
Supersized | Nolimit | Lars | Jakob, Oliver | Artem | Artem | Lars | Jasper | Sumit | Himanshu, Arjun | Bogdan |  | 2025-12-22 |  |  | 2026-02-10 |  | 215.79 |  |  | 618 | 12345x | S | Cert moved from 16/12 to 19/12 but server deployed to cert on 16/12
San Quentin Manhunt (Stake) | BESPOKE | Per | Anna, (Seb) | Carlo Felipe, Doro | Hannah, Gabriele | David | Iman | Alexandru, Shivangi | Anil |  |  | 2025-12-16 |  |  | 2026-02-12 | UNREG - any certs? Stamp? | 244.38 |  |  | 530 | 46532x | M
The Crypt 2 | Nolimit | Per | Jelina, (Seb) | Kit | Sudha, Gabriele | Gum | Iman (Rashin) | Shivangi | Shamim |  |  | 2026-01-20 |  |  | 2026-03-03 |  | 168.06 |  |  | 470 | 31248x | M
Catfish Hunters | Nolimit | Jasper | Shivay | Vijay, Aniruddha | Varun, Hironmoy | Victor F | Jasper | Ankit | Himanshu |  |  | 2026-01-20 |  |  | 2026-03-17 |  | 206.84 |  |  | 372 | 20000x | M
Pünk Rocker 3 | Nolimit | Ben/Bjarne | Akash | Annie | Annie, Viktoriia | David | Jasper | Dan, Nilesh | Himanshu |  |  | 2026-02-09 |  |  | 2026-04-07 |  |  |  |  | 441 | 19089x | M
San Quentin Manhunt - global release | Nolimit | Per | Anna, (Seb) | Carlo Felipe | Hannah, Gabriele | David/Gum | Iman | Shivangi |  |  |  | 2026-02-24 |  |  | 2026-04-21 |  |  |  |  | 530 | 46532x | M-S
Bonus Junkie | Labs | Wai | Antonio, Utkarsh (Wålekvist) | Anders | Prakash, Hironmoy | Victor F | Christian | Claudia,Priya, Ludwig | Anil |  |  | 2025-11-24 |  |  | 2026-04-23 | UNREG - Stake exclusive |  |  |  | - | 481665x | L
Tombstone Begins | Nolimit | Wai, Gaurav | Anubhav | Oliver Morit (Carlo) | Khei, Prakash | Gum | Jasper | Nilesh | Anil, Arjun |  |  | 2026-02-06 |  |  | 2026-05-12 | Moved til May |  |  |  | 309 | 20000x | M
True Grit Redemption 2 | Nolimit | Ben | Jerker, Utkarsh | Nico | Nico, Viktoriia/Gabriele | Reynir | Christian | Claudia | Shamim |  |  | 2026-03-10 |  |  | 2026-05-26 | [5 empty] | 34000x | M
Tanked 3: First Blood 2 | Nolimit | Tiger | Ning | Nico, Oliver | Gustav | Reynir | Jasper/Christian | Sumit | Anil, Himanshu |  |  | 2025-03-31 |  |  | 2026-06-09 | Cert server again |  |  |  | 140 | 25584x | M-L
Soaked By Seamen | Nolimit | Jasper | Andy, Oliver | Johan, Anoop | Gustav (Sudha) | Victor F | Jasper | Sumit | Himanshu, Arjun |  |  | 2026-04-07 |  |  | 2026-06-23 | [5 empty] | 20000x | S
AFK Airport Security | Nolimit | Bjarne | Virender, Lakshay | Jan | Lars L, Varun | Gum | Yuhan | Shivangi, Alex | Shamim, Arjun |  |  | 2026-04-14 |  |  | 2026-07-07 | [6 empty] | S
Duck Hunters 2 | Nolimit | Jasper | Sukhdev | Aniruddha, Vijay | Prakash, Hannah | David | Jasper | Ankit | Anil |  |  | 2026-05-19 |  |  | 2026-07-28 | [6 empty] | M
Outsourced 2 - Balkan Engineering | Express | Lars | Jelina (Seb) | Doro | Gabriele | Lars | Affe | Dan, Nilesh | Shamim |  |  | 2026-05-12 |  |  | 2026-08-11 | [6 empty] | S
Six Feet Under | Nolimit | Jasper | Pradeep | Javi, Anders | Hannah |  | Jasper | Claudia |  |  |  | 2026-06-16 |  |  | 2026-08-25
Borken | Nolimit | Bjarne | Utkarsh | Denise | Sudha |  | Christian |  |  |  |  | 2026-06-30 |  |  | 2026-09-08 | [6 empty] | S
FITH4 | Nolimit | Wai | Anna | Tetiana | Gabriele (Ed) |  | Rashin/Iman |  |  |  |  | 2026-06-30 |  |  | 2026-09-22 | [6 empty] | S
Bowel of Beelzebub | Over the Limit | Lars | Oliver | Artem | Artem | Lars | Affe |  |  |  |  | 2026-07-14 |  |  | 2026-10-06
Feed em to the pigs (NOT BIZARRE) | Nolimit | Per |  | Carlo, Noreus |  |  | Wai, Math X | [7 empty] | 2027-01-05 | [6 empty] | M
Gator Hunters 2 | Nolimit | Jasper | Shivay | Kit |  |  | Jasper |  |  |  |  | 2026-08-18 |  |  | 2026-11-24
Concept X | Nolimit | Lars | Jelina, (Seb) | Doro | Gabriele | [9 empty] | 2026-12-08 | [6 empty] | M
Broligarchs | Labs | Ben | Ning | Calle | Calle, Joel | Victor F | Wai/Shivang | Priya, Ludwig | Anil |  |  | 2026-06-17 |  |  | 2027-01-05 | [5 empty] | 25120x | M
Mental III | Over the Limit | Wai, Lars | Virender | Anoop | Anoop | Lars | Yuhan |  |  |  |  | 2026-06-30 |  |  | 2027-02-09 | ICE SHOWCASE | [5 empty] | M
Maggot | Nolimit | Gaurav/Lars | Gaurav | Vijay | Prakash | Lars | Pankaj |  |  |  |  | 2026-07-21 |  |  | 2027-04-20
TheCryptMickeyMouseClub (Exploring) | Express | Wai | Jakob | Carlo/Francell | Ed |  | Iman |  |  |  |  | 2026-06-30 |  |  | 2026-09-08 | [6 empty] | M
TO COME/ON HOLD
Bass to Mouth | Nolimit | Lars
Alien Lean | Express | Lars | Andy | Artem | Artem | Lars | Andy/Yuhan | [7 empty] | 2027-03-09 | [6 empty] | S
Medieval on your ass | Over the Limit | Jonas |  | Francell? | [10 empty] | 2027-03-23
Dental | Over the Limit | Lars |  | Calle |  | Lars | [8 empty] | 2027-01-05
Kenneth is Erected | Over the Limit | Lars |  |  |  |  | Math VTurk
Death By Bingo | Express | Lars | Oliver | Johan | Johan, Gabriele? | Lars | Wai/Rashin
Dead Canary Straight-Up Reels | Nolimit | [13 empty] | 2027-02-23 | [6 empty] | M
Flight Mode 2 - Hijacked | Nolimit | Lars | Jakob |  |  |  | Affe | [7 empty] | 2027-01-19
Masked Swinger | Over the Limit | Ben | Pradeep | Javi |  |  | Christian/Shivang | [7 empty] | 2027-04-06 | [6 empty] | M
Darkside of the Moo
Horseface | Express | Lars |  | Calle |  |  | Wai
Skins - Per. Outsourced. DH, FITH2, SQ, Nine to Five, etc. | Vanilla | Per
Kenneth must die light skin | Reskin | Wai |  | Deepak(Vijay) |  |  | Iman | [14 empty] | M
Vanilla Duck Hunters US-skin | Nolimit | Per |  | Carlo
Explore: Das xBoot 2, True Grit & Dead Canary (straight!) continuation concepts
Brainstorm concepts | Studio | Followup to | Character reuse | Comment | Type | Links
Trespassing (Nolimit) | Nolimit |  |  | us irony
Somalian Boattrip | Over the Limit
Soaked by Seamen (Seamen cont.) | Nolimit
Runaway Train | Over the Limit
Flight Mode 2: Hijacked | Nolimit
Brutiest Force: Die with Avengence | Nolimit
Dude, where's my swamp? | Nolimit
Alcatraz (Nolimit) Swamp Alcatraz (30s) | Nolimit |  |  | San Quentin follow up
Undercover (Nolimit) | Nolimit |  |  | Donny brasco
No escape (saw feeling, over the limit) | Over the Limit
Graveyard shift (nolimit) | Nolimit |  |  | janitor on gravyars working
Before the race (Nolimit) | Nolimit
Haunted |  |  |  | Krisztians/Sergiu concept -
Falling Down |  |  |  | Mental breakdown from daily life
Saatana Perkele xHelveti | Labs
Death by Dildo (Ken 2) (OTL)
Bail bondsman (Nolimit) | Nolimit
Insta moment | Labs | Picture Perfect? |  | Full irony, Perfect picture, good looking girl, filter
Finders Keepers |  |  |  | Old school drifters
Last Resort
Insomnia
Crash Games (3 skins) | Labs
OnlyCash |  |  |  | Irony of OnlyFans
Guillotine |  |  |  | Guillotine - France Revolution era, Wigs, Royalty with messed up Makeups
Furry Fury
Beyond Badass - 80's action heroes
BarbieBarian (They/Them) |  |  |  | A trans barbarian who strikes down everyone who is not politically correct (probably BarbyBarian as name)
From Duck Till Dawn
Game suggestions
Money Maker |  |  |  | Forger, fake money printing - "Catch me if you can"
Purgatory
Douchebag
Dead end Joe |  |  |  | Dead end jobs for average dudes, mainly mascots after hours (Joe Dirt)
All Inclusive
My name is BOB
Inspiration Suggestions + Mechanics needed
Lazer Tazer
Hold n' Spin for US (FITH3 + 1 more)
Coin Collect (Tanked 2 + 1 more Wai)
Fake Jackpot (The Crypt 2)
Black Scatter (The Crypt 1 or 2)
Duck Hunters RIP/Begins
Formulas:
START DATE = [LIVE DATE]-6*30

## Teams
Name | Main role - estimation | Comment | Office | Competence | # of | Target | Diff |  | WORKFLOW
Pankaj | Client Developer Framework |  | India | Client Developer Sr | 12 | 15 | 3 |  | Progress | Concept | Game Start | Game Mid | Cert | Game Finish
Jonas W | Client Developer Framework |  | Sthlm | Client Developer Jr | 6 | 3 | -3 |  | Product | Vision
Anubhav | Client Developer Jr |  | India | GFX 2D Sr | 12 | 10 | -2 |  | GFX | Concept GFX
Gaurav | Client Developer Jr |  | India | GFX 2D Jr | 7 | 3 | -4 |  | Client Developer |  | Client up
Lakshay | Client Developer Jr |  | India | GFX All Sr | 2 | 3 | 1 |  | Animation
Sukhdev | Client Developer Sr |  | India | GFX All Jr | 0 | 1 | 1 |  | Math | Mock server | Base + FS
Shivay | Client Developer Sr |  | India | GFX Animation Sr | 9 | 8 | -1 |  | QA |  |  | Intro | Automation
Virender | Client Developer Sr |  | India | GFX Animation Jr | 1 | 4 | 3
Akash | Client Developer Sr |  | India | Math Sr | 2 | 3 | 1
Utkarsh | Client Developer Sr |  | India | Math Jr | 4 | 2 | -2
Pradeep | Client Developer Sr |  | India | Product Sr | 3 | 5 | 2
Jakob | Client Developer Sr |  | Sthlm | Product Jr | 3 | 2 | -1
Jelina | Client Developer Jr |  | Sthlm | QA Automation Sr | 3 | 3 | 0
Andy | Client Developer Jr |  | Sthlm | QA Automation Jr | 1 | 1 | 0
Anna | Client Developer Sr |  | Sthlm | QA Sr | 8 | 7 | -1
Antonio | Client Developer Sr |  | Sthlm | QA Jr | 3 | 2 | -1
Jerker | Client Developer Sr |  | Sthlm | Sound Sr | 3 | 2 | -1
Ning | Client Developer Sr |  | Sthlm | Sound Jr | 2 | 1 | -1
Oliver | Client Developer Sr |  | Sthlm
Seb | Client Developer Jr |  | Sthlm
Aniruddha | GFX 2D Jr |  | India
Deepak P | GFX 2D Jr |  | India | Current Development | # est. games / year | Target # of games: | 24
Noreus | GFX 2D Jr |  | Other | Client Developer Sr | 2 | 24
Marco | GFX 2D Jr |  | Romania | Client Developer Jr | 1 | 6 | 30
Annie | GFX 2D Jr |  | Sthlm | GFX 2D Sr | 1.7 | 20.4
Tetiana | GFX 2D Jr |  | Sthlm | GFX 2D Jr | 1 | 7
Dorottia | GFX 2D Jr |  | Sthlm | GFX All Sr | 2 | 4
Anoop | GFX 2D Sr |  | India | GFX All Jr | 1.3 | 2.6 | 34
Vijay | GFX 2D Sr |  | India | GFX Animation Sr | 3 | 27 |  | -2
Carlo | GFX 2D Sr |  | Other | GFX Animation Jr | 2 | 2 | 35.6
Carlo Felipe | GFX 2D Sr |  | Other | Math Sr | 5 | 10
Francell | GFX 2D Sr |  | Other | Math Jr | 3 | 12 | 22
Oliver Morit | GFX 2D Sr |  | Other | Product Sr | 6 | 18
Calle | GFX 2D Sr |  | Sthlm | Product Jr | 3 | 9 | 27
Anders | GFX 2D Sr |  | Sthlm | QA Automation Sr | 8 | 24
Jan | GFX 2D Sr |  | Sthlm | QA Automation Jr | 6 | 6 | 30
Javi | GFX 2D Sr |  | Sthlm | QA Sr | 4 | 32
Johan H | GFX 2D Sr |  | Sthlm | QA Jr | 4 | 12 | 44
Kit | GFX 2D Sr |  | Sthlm | Sound Sr | 9 | 27
Artem | GFX All Sr |  | Sthlm | Sound Jr | 6 | 12 | 39
Nico | GFX All Sr |  | Sthlm | TOTAL |  |  | 22
Hironmoy | GFX Animation Jr |  | India
Prakash | GFX Animation Sr |  | India
Varun | GFX Animation Sr |  | India
Ed | GFX Animation Sr |  | Other | Future Development | # est. games / year | Target # of games: | 24
Hannah | GFX Animation Sr |  | Other | Client Developer Sr | 2 | 30
Khei | GFX Animation Sr |  | Other | Client Developer Jr | 1 | 3 | 33
Viktoriia | GFX Animation Sr |  | Other | GFX 2D Sr | 1.7 | 17
Sudha | GFX Animation Sr |  | Sthlm | GFX 2D Jr | 1 | 3
Gabriele | GFX Animation Sr |  | Sthlm | GFX All Sr | 2 | 6
Gustav | GFX Animation Sr |  | Sthlm | GFX All Jr | 1.3 | 10.4 | 36.4
Christian | Math Jr |  | Sthlm
Wai | Math Jr | Math: 3 games/year | Sthlm | GFX Animation Sr | 3 | 12
Viktor L | Math Jr |  | Sthlm | GFX Animation Jr | 2 | 6 | 34.4
Yuhan | Math Jr |  | Sthlm | Math Sr | 5 | 10
Iman | Math Sr |  | Sthlm | Math Jr | 3 | 15 | 25
Jasper | Math Sr |  | Sthlm | Product Sr | 6 | 12
Per | Product Jr | PO: 3 games/year | Sthlm | Product Jr | 3 | 9 | 21
Wai | Product Jr | PO: 3 games/year | Sthlm | QA Automation Sr | 8 | 56
Jasper | Product Jr | PO: 3 games/year | Sthlm | QA Automation Jr | 6 | 12
Ben | Product Sr |  | Sthlm | QA Sr | 4 | 28
Bjarne | Product Sr |  | Sthlm | QA Jr | 4 | 8 | 36
Lars | Product Sr |  | Sthlm | Sound Sr | 9 | 18
Arjun | QA Automation Jr |  | India | Sound Jr | 7 | 7 | 25
Anil | QA Automation Sr |  | India | TOTAL |  |  | 21
Himanshu | QA Automation Sr |  | India
Mohammad Shamim | QA Automation Sr |  | India
George | QA Backend |  | Romania
Pankaj C | QA Framework |  | India
Shivangi | QA Sr |  | India
Dan | QA Jr |  | Romania
Alexandru P | QA Jr |  | Romania
Ankit | QA Sr |  | India
Nilesh | QA Sr |  | India
Sadhika | QA Sr | Maternity leave | India
Sumit | QA Sr |  | India
Priyanka | QA Jr | Under training | India
Claudia | QA Sr |  | Romania
Denis | QA Sr |  | Romania
Priya | QA Sr |  | Sthlm
Lars | Sound Jr |  | Sthlm
Victor F | Sound Jr |  | Sthlm
Reynir | Sound Sr |  | Sthlm
Viktor O | Sound Sr |  | Sthlm
David | Sound Sr |  | Sthlm
On the bench

## Game Types 2025
GAME NAME | TYPE | PRODUCT | LIVE DATE
Devil's Crossroad | Labs | Wai/Gary | 2024-01-09 |  |  | Special Olympics (Crash game) | Express | Lars
Land of the free | Nolimit | Lars | 2024-01-23 |  |  | FITH 3 | Nolimit | Wai
D Day | Nolimit | Krisztian | 2024-02-13 |  |  | Carnage 2 | Nolimit | Tiger
FITH 2 | Nolimit | Gary | 2024-02-20 |  |  | Bangkok Hilton | Nolimit | Per
Possessed | Nolimit | Krisztian | 2024-03-05 |  |  | Medievil on your ass | Over the Limit | Jonas
Brick Snake 2000 | Labs | Lars | 2024-03-21 |  |  | Mental-ish (Avalanche) | Nolimit | Tiger
Tombstone No Mercy | Nolimit | Per/Wai | 2024-04-16 |  |  | The Crypt 2 | Nolimit | Per
Kenneth must die | Over the limit | Jonas | 2024-05-07 |  |  | Beyond Badass - Broforce | Nolimit
Loner | Nolimit | Lars | 2024-05-21 |  |  | Das xBoot 2 | Nolimit
Deadwood RIP | Over the limit | Per/Wai | 2024-06-04
Beheaded | Labs | Seb | 2024-06-18
Punk Rocker 2 | Nolimit | Tiger | 2024-07-09
Apocalypse Super xNudge | Nolimit | Krisztian | 2024-07-23
Outsourced | Labs | Lars | 2024-08-06
Stockholm Syndrome | Nolimit | Wai/Calle | 2024-08-20
Skate or Die | Nolimit | Lars | 2024-09-10
San Quentin 2: Death Row | Over the Limit | Wai/Per | 2024-09-24
Brute Force | Nolimit | Krisztian | 2024-10-08
Blood & Shadow 2 | Nolimit | Krisztian | 2024-10-22 | Game type 2024
Outsourced: Slash game | Rapid | Lars | 2024-11-05 | Labs | 5
Carnage | Labs-Nolimit | Tiger | 2024-11-19 | NLC | 14
Outsourced: Nightshift (claw game) | Rapid | Lars | 2024-11-26 | OTL | 3
Highway to Hell (old Somali) | Nolimit | Per | 2024-12-03 | Rapid | 2
xWays Hoarder 2 | Nolimit | Tiger | 2024-12-17 | TOTAL | 24
Dumpster Diet | Labs | Tiger/Jasper | 2025-01-14
Tombstone Slaughter: El Gordos Revenge | Over the Limit | Per | 2025-01-28 | Game type 2025
Wanted: Dead, Dead or Dead | Nolimit | Lars | 2025-02-11 | Labs | 5
PotSlots - Decadence (separate release) | Rapid | Tiger | 2025-02-18 | NLC | 15
Game XXX - Japanese? | Nolimit | Krisztian | 2025-02-18 | OTL | 4
PotSlots - Dungeon | Rapid | Tiger | 2025-02-25 | Rapid | 4
Sequel - Mental 2 | Over the Limit | Lars/Jonas | 2025-03-04 | TOTAL | 28
Home of the Brave | Nolimit | Lars | 2025-03-18
Bonus Hunter (Cart) | Nolimit | Wai | 2025-04-08
Fake Jackpot Game | Labs | Tiger | 2025-04-22
Sequel - FITH 3 | Nolimit | Wai | 2025-05-06 | MARKET SPECIFIC GAMES & MECHANICS
Loner Mini Games (separate release) | Rapid | Lars | 2025-05-13 | Hold n' Spin
Mental-ish | Nolimit | Tiger | 2025-05-20 | Fake Jackpot
Fishing Type Game - UG-style | Nolimit | Krisztian | 2025-06-03 | Fish games
Sequel - Das xBoot 2 | Nolimit |  | 2025-06-17 | Avalanche Games (The Crypt 2 - Mental-ish?)
OTL XXX | Over the Limit |  | 2025-07-08
Tanked | Nolimit | Lars | 2025-07-22 | ADDITIONAL POTENTIAL SEQUELS
Hold n Spin-games | Nolimit |  | 2025-08-05 | Carnage
Nolimit XXX | Nolimit |  | 2025-08-19 | Ken Must Die
Sequel - Pünk Röcker 3 | Nolimit | Tiger | 2025-09-09
Labs YYY | Labs |  | 2025-09-23
Nolimit YYY | Nolimit |  | 2025-10-07
Nolimit ZZZ | Nolimit |  | 2025-10-21
OTL YYY | Over the Limit |  | 2025-11-04
Sequel - XXXX | Nolimit |  | 2025-11-18
Labs XXX | Labs |  | 2025-12-02
NOLIMIT WWW | Nolimit |  | 2025-12-16